## risk_overview
Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact | Risk Factor (sort) | Risk Mitigation | Person in Charge of Tracking
loss of teammembers | Possibility of loosing menbers because of illness/exmatrikulation or other issues during the project (Corona) | 8 | 9 | 72 | stay at home
lack of skills | complex technology, teammembers have to get used to software | 6 | 8 | 48 | do tutorials, take time to get used to technology
lack of time | a lot of exercises have to be implemented in a limited period of time | 9 | 9 | 81 | time management, spend freetime
tool failure | software tools, IDEs or other development tools break down and prevent an effective working flow | 5 | 6 | 30 | work with several tools, take common and supported tools
financial issues | missing money for the project | 1 | 1 | 1
users resistance | users don`t like the idea/architecture of our app which leads to the need of renew it | 4 | 5 | 20 | a lot of discussions, analyse the users expectations
change of payment system | tha payment system changes radically so that the app bases on outdated factors | 1 | 4 | 4 | make the software architecture adaptable
change of smartphone architecture | the architecture of smartphone (apps) changes radically so that the app is outdated | 1 | 9 | 9 | make the software architecture adaptable
milstones not defined | there are no goals and usecases defined | 3 | 4 | 12 | define some
unspecified way of working | teammembers have no spacified way of working; they don´t know which usecases they have to implement and which they don´t have to | 5 | 5 | 25 | specify a general way of working in team
inexperienced managers | the manager doesn´t have enough experience to lead the team effectively | 8 | 4 | 32 | team could manage itself, every member is allowed to give advises
ineffective communication | teammembers do not state thier progress and work on same topics | 6 | 8 | 48 | use simple communication tools since corona prevents social contact
progress not saved | the progress of teammembers´ work is not saved | 3 | 10 | 30 | use version controle software -> comit early, commit often
unstable politics | changes in politics influence the project negatively | 6 | 1 | 6 | nothing to do
change of team management | the team manager changes which leads to a chaotic management | 6 | 3 | 18 | make an appropriate handover of all subjects/jobs
unreliability of team member | teammembers are not reliable and do not fullfill their exercises | 1 | 8 | 8 | control each other in some way. Have discussions about progress, help each other if there are problems
unable to work productively | some systems or software tool break down which makes a productive way of working impossible | 7 | 8 | 56 | share skills of tool with the team/whole class - know how transfer

## risk_factor
Severity of consequences
|  | low | medium | high
Frequency of Scenario | high | medium | high | high
| medium | low | medium | high
| low | low | low | medium