## risk_overview
Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact | Risk Factor (sort) | Risk Mitigation | Person in Charge of Tracking
loss of teammembers | Possibility of loosing menbers because of illness or other issues during the project | medium - high | 9
lack of skills | complex technology, teammembers have to get used to software | low | 8
lack of time | a lot of exercises have to be implemented in a limited period of time | high | 9
tool failure | software tools, IDEs or other development tools break down and prevent an effective working flow | medium | 6
financial issues | missing money for the project | low | 1
users resistance | users don`t like the idea/architecture of our app which leads to the need of renew it | medium | 5
change of payment system | tha payment system changes radically so that the app bases on outdated factors | low | 4
change of smartphone architecture | the architecture of smartphone (apps) changes radically so that the app is outdated | low | 9
milstones not defined | there are no goals and usecases defined | low | 4
unspecified way of working | teammembers have no spacified way of working; they don´t know which usecases they have to implement and which they don´t have to | low | 5
inexperienced managers | the manager doesn´t have enough experience to lead the team effectively | medium | 4
ineffective communication | teammembers do not state thier progress and work on same topics | medium | 8
progress not saved | the progress of teammembers´ work is not saved | low | 10
unstable politics | changes in politics influence the project negatively | low | 1
change of team management | the team manager changes which leads to a chaotic management | low | 3
unreliability of team member | teammembers are not reliable and do not fullfill their exercises | low | 8
unable to work productively | some systems or software tool break down which makes a productive way of working impossible | medium - high | 8

## risk_factor
Severity of consequences
|  | low | medium | high
Frequency of Scenario | low | medium | high | high
| medium | low | medium | high
| high | low | low | medium